## OC25
PROJECT NAME: |  |  |  |  | CREATION DATE:
PROJECT LOCATION: |  |  |  |  | SCO APPROVAL DATE:
AGENCY OR INSTITUTION: |  |  |  |  | BIENNIUM:
PROJECT DESCRIPTION: (Written description of project scope, scale, and schedule including the current status as of this OC-25, i.e. pre-funding, funded, advance planning, design phase, etc.)
ESTIMATED PROGRAM CONSTRUCTION HARD COST ON CREATION DATE (Match Project Description)
ITEM | DESCRIPTION |  | QTY | UNIT | COST PER UNIT | TOTAL
SITE CONSTRUCTION-NEW (Insert Additional Rows as Required)
Site |  |  |  | Acre |  | 0
Site |  |  |  | LF |  | 0
Site |  |  |  | Parking Space |  | 0
CONSTRUCTION-NEW (Insert Additional Rows as Required)
Demolition |  |  |  | GSF |  | 0
Construction-New |  |  |  | GSF |  | 0
Construction-New |  |  |  | GSF |  | 0
CONSTRUCTION-RENOVATION (Insert Additional Rows as Required)
Construction-Renovation |  |  |  | GSF |  | 0
Construction-Renovation |  |  |  | GSF |  | 0
Sub-Total Program Construction Cost: | (Total of all expected first-tier subcontractor bid packages) |  |  |  |  | 0
CMR/GC Cost: | 15% | (14%-20% of Sub-Total Program Construction Cost) |  |  |  | 0
A. ESTIMATED PROGRAM CONSTRUCTION COST: | [5 empty] | 0
B. APPLY 90/10 RULE TO 'A' ABOVE: | 90% |  |  |  |  | 0
OWNER'S ESTIMATED SOFT COSTS (Percentage of 'A' Above or Lump Sum)
ITEM | % or LS | DESCRIPTION |  |  |  | TOTAL
ADVANCE PLANNING | 1% | (% of 'A' Above-Includes programming, survey/topo/utilities, cost estimate) |  |  |  | 0
DESIGN FEE | 10% | (% of 'A' Above) |  |  |  | 0
PRECONSTRUCTION SERVICES | 1% | (1% of 'A' Above for CM@Risk) |  |  |  | 0
COMMISSIONING CONSULTANT | 0.5% | (0.5% simple; 1.0% moderate; 1.5% complex) |  |  |  | 0
SPECIAL INSPECTIONS & TESTING CONSULTANT | 0.5% | (0.5% simple; 1.0% moderate; 1.5% complex) |  |  |  | 0
SUSTAINABILITY | 2% | (4% LEED Platinum/4 Globes; 3% LEED Gold/3 Globes; 2% LEED Silver/2 Globes; 1% LEED Certified/1 Globe) |  |  |  | 0
CONSTRUCTION PHASE CONTINGENCY | 3% | (% of Estimated Construction Costs [3% New or 5% R&R]) |  |  |  | 0
90/10 RULE OWNER RESERVE FUNDS | 10% |  |  |  |  | 0
ESCALATION ANALYSIS: |  | Project Schedule Milestones | Months
Funding Process |  | 1. OC-25 Creation Until Project Funded
Designer Selection |  | 2. Designer RFQ/Interview/Selection
Design Phases |  | 3. Design Phases Duration
Construction |  | 4. Bid Advertisement to Midpoint of Construction |  |  | Monthly Escalation
ESCALATION: BLS PPI ANNUAL INFLATION RATE | 5% | Total Months of Escalation: | 0 |  | 0.4167% | 0
MISCELLANEOUS | LS | Permits, Fees, Printing, Legal
FURNITURE BY OWNER | LS | Chairs, Desks, Tables, Workspace (Add 1.75% of Cost When Using P & C)
EQUIPMENT BY OWNER | LS | Lab, Pantry, Business
STATE OR INSTITUTION IT EQUIPMENT | LS | Data Center, Data Recovery, LAN
AV and TECHNOLOGY | LS | AV/Technology Equipment and Installation
TEMPORARY SPACE REQUIREMENT | LS | Relocation/Storage/Lease Space
LAND REQUIREMENT | LS | Acquisition Cost
C. SUB-TOTAL OWNER'S ESTIMATED SOFT COST: | [5 empty] | 0
|  | Year of Initial Estimate: | 2025
D. ESTIMATED TOTAL PROJECT COSTS ( B + C ) : | [5 empty] | 0
|  |  | 2026 | 2027 | 2028 | 2029
| Indicates a Required Field to be Completed by Estimator |  | 5% | 5% | 5% | 5%
|  |  | 0 | 0 | 0 | 0
Automatic Escalation Will Occur Annually on October 1 With No Program Changes
APPROVED BY: |  | TITLE: |  |  | DATE: